## Features
Fields
Feature Id | Unique id for sorting, searching, and grouping features
Description | Sufficient text to fully explain the how the feature works
Feature/Task Tags
Status Tags | Status meaning
* | Stretch Goal - Dependent on game feel / results post implementation
% | Not originally planned.
! | Highest priority
x | Removed from original plan.
Feature Id | Feature Area | Description
1 | Input | Player controls Paddle with Mouse Movement.
2 | UI/Input | Player can use the Menu using Mouse or Keyboard.
3 | UI/Input | Non Persistent High Score system where players can enter their name for up to maximum of 10 top scores.
4 | UI | Main menu with the some sub menus like settings, controls (only for display) and high score menu.
5 | Game - Data | Data driven gameplay components like assets - tile, paddle, ball, tile types, paddle base size, paddle max size, etc.
6 | Game - Juice | Some basic ball and paddle powerups like expand paddle, shrink paddle, increase ball size, decrease ball size, mutiply balls.
7 | Game - Physics | Simpler Physics system for collisions between ball and paddle and ball and the tiles. (the current system lacks performance).
8 | Testing | Stress testing Physics system for performance.
9 | Engine | Adding in a 2D-Particle system.
10 | Game - Juice | Integrating Particle system with tiles. Tile based particle effect on collision.
11 | Game - Juice | Screen-Shake effects. Screen Shake on ball-tile collision.
12 | Game - Level | Finalizing 3 levels / level generation technique(painting the level or Pattern based PCG technique).
13 | Game - Mechanics | Scoring mechanics based on how the tile is destroyed (math for how the score is calulated based on chaining and tile collison).
14 | UI | In game HUD to display score, level number and current lives.
15 | Game - Juice | Finalizing Powers (complete set of all the ball & paddle powerups/powerdowns).
16 | Game - Juice | Integrating Particle system with the ball (particle effects for ball launch and collisoin with different tiles).
17 | Game - Level | Environmental Hazards (like a lava tile that destroys the ball or reduces score every time you collide with it).
18 | Game - Level | PCG for level generation (I’d like there to be patterns rather than random worms).
19 | Game - Data | Saving High Score Data.
20 | UI | Refining Menus.
21 | UI | Game over screen displaying your score and displaying all the high scores where you can enter name if you beat a high score and a return to main menu button.
22 | Game - Mechanics | RNG based Power Drop on tile breaks.
23 | Game - Audio | Adding in audio effects for different tiles breaking and background audio.
24 | Game - Audio | Audio for the Menus.
25 | Game - Level | Adding in More levels
26 | Game | Final polish and bug fixing.
27 | Game - Level | Initial Test Level Setup
28 | Testing | General Gameplay Testing
29 | UI | Pause Menu
30 | UI | Tutorials Menu dislaying various tile types and powers.
9999 | Miscellaneous | Corresponds to Engine Code/Slice of Life code that does not directly effect gameplay

## Milestones
Fields
Feature Id | Unique id for sorting, searching, and grouping features
Description | Sufficient text to fully explain the how the feature works
Feature/Task Tags
Status Tags | Status meaning
* | Stretch Goal - Dependent on game feel / results post implementation
% | Not originally planned.
! | Highest priority
x | Removed from original plan.
Milestones | Dates
Milestone 1 | 2020-06-15
Milestone 2 | 2020-06-29
Milestone 3 | 2020-07-13
Final Deliverable | 2020-07-21
Milestones | Feature ID | Feature Area | Description
Milestone 1 | 5 | Game - Data | Data driven gameplay components like assets - tile, paddle, ball, tile types, paddle base size, paddle max size, etc.
Milestone 1 | 6 | Game - Juice | Some basic ball and paddle powerups like expand paddle, shrink paddle, increase ball size, decrease ball size, mutiply balls.
Milestone 1 | 7 | Game - Physics | Simpler Physics system for collisions between ball and paddle and ball and the tiles. (the current system lacks performance).
Milestone 1 | 8 | Testing | Stress testing Physics system for performance.
Milestone 1 | 27 | Game - Level | Initial Test Level Setup
Milestone 1 | 28 | Testing | General Gameplay Testing
Milestone 1 | 10 | Game - Juice | Integrating Particle system with tiles. Tile based particle effect on collision.
Milestone 1 | 11 | Game - Juice | Screen-Shake effects. Screen Shake on ball-tile collision.
Milestone 1 | 12 | Game - Level | Finalizing 3 levels / level generation technique(painting the level or Pattern based PCG technique).
Milestone 1 | 16 | Game - Juice | Integrating Particle system with the ball (particle effects for ball launch and collisoin with different tiles).
Milestone 1 | 23 | Game - Audio | Adding in audio effects for different tiles breaking and background audio.
Milestone 2 | 29 | UI | Pause Menu
Milestone 2 | 2 | UI/Input | Player can use the Menu using Mouse or Keyboard.
Milestone 2 | 3 | UI/Input | Non Persistent High Score system where players can enter their name for up to maximum of 10 top scores.
Milestone 2 | 4 | UI | Main menu with the some sub menus like settings, controls (only for display) and high score menu.
Milestone 2 | 13 | Game - Mechanics | Scoring mechanics based on how the tile is destroyed (math for how the score is calulated based on chaining and tile collison).
Milestone 2 | 14 | UI | In game HUD to display score, level number and current lives.
Milestone 2 | 17 | Game - Level | Environmental Hazards (like a lava tile that destroys the ball or reduces score every time you collide with it).
Milestone 2 | 18 | Game - Level | PCG for level generation (I’d like there to be patterns rather than random worms).
Milestone 2 | 28 | Testing | General Gameplay Testing
Milestone 3 | 19 | Game - Data | Saving High Score Data.
Milestone 3 | 20 | UI | Refining Menus.
Milestone 3 | 21 | UI | Game over screen displaying your score and displaying all the high scores where you can enter name if you beat a high score and a return to main menu button.
Milestone 3 | 22 | Game - Mechanics | RNG based Power Drop on tile breaks.
Milestone 3 | 24 | Game - Audio | Audio for the Menus.
Milestone 3 | 25 | Game - Level | Adding in More levels
Milestone 3 | 28 | Testing | General Gameplay Testing
Final Deliverable | 26 | Game | Final polish and bug fixing.
Final Deliverable | 28 | Testing | General Gameplay Testing
Final Deliverable | 29 | UI | Pause Menu
Final Deliverable | 30 | UI | Tutorials Menu dislaying various tile types and powers.

## Backlog
Fields
Task Id | Unique id for sorting, searching, and grouping tasks
Status | Current status of this task, see legend
Estimate | Estimated time to complete this task, in hours
Actual | How much time was actually spent on this task, in hours
Feature Id | Unique id for sorting, searching, and grouping features
Description | Sufficient text to fully explain the how the feature works
Status Codes | Status meaning |  |  |  |  | Feature/Task Tags | Tag meaning
O | Not Started |  |  |  |  | * | Stretch Goal - Dependent on game feel / results post implementation
/ | In Progress |  |  |  |  | % | Not originally planned.
X | Complete |  |  |  |  | ! | Highest priority
< | Sent to backlog |  |  |  |  | x | Removed from original plan.
> | Carried to next sprint
D | Deleted
Task ID | Status | Task Tags | Estimate | Actual | Feature Area | Feature ID | Task Description
1 | X |  | 3 | 2.58 | Game - Level | 27 | Initial Test Level Setup
2 | / |  | 2 | 2.33 | Game - Data | 5 | Data driving Tiles, Paddle & Ball
3 | D | x | 2 | 0.5 | Game - Physics | 7 | Simpler Physics system for collisions between ball and paddle and ball and the tiles.
4 | / |  | 0.5 | 0.5 | Input | 1 | Player controls Paddle with Mouse Movement.
5 | D | x | 2 | 0 | Testing | 8 | Updating Test Level & Stress testing Physics system for performance.
6 | 0 |  | 4 | 0 | Miscellaneous | 9999 | Basic UI System for Buttons and Labels.
7 | 0 |  | 1.5 | 0 | UI | 4 | Main menu with the some sub menus like settings, controls ( only for display ).
8 | 0 |  | 2 | 0 | UI | 4 | Adding in first pass of menu assets to match the theme.
9 | 0 |  | 1 | 0 | UI | 4 | High score menu.
10 | 0 |  | 1 | 0 | UI/Input | 3 | Input Name on High Score Menu
11 | 0 |  | 1 | 0 | UI/Input | 2 | Player can use the Menu using Mouse or Keyboard.
12 | 0 |  | 1.5 | 0 | Game - Juice | 6 | Some basic ball and paddle powerups like expand paddle, shrink paddle, increase ball size, decrease ball size, mutip
13 | 0 |  | 4 | 6 | Engine | 9 | Implement 2D - Particle System
14 | 0 |  | 1 | 0.5 | Game - Juice | 10 | Create Particle Effects on ball-Tile Collision.
15 | 0 |  | 2 | 0 | Game - Juice | 16 | Create Varying Particle Effects for different tiles.
16 | 0 | * | 2.5 | 0 | Game - Level | 18 | Implement & Test Pattern Based PCG Level Generation.
17 | 0 |  | 1.5 | 0 | Game - Level | 12 | Adding in at least 3 more levels.
18 | 0 |  | 0.75 | 0 | Game - Level | 12 | Hook up all the levels.
19 | 0 |  | 0.5 | 0 | Game - Juice | 11 | Screen Shake effect for ball-tile collision.
20 | 0 |  | 0.75 | 0 | Game - Mechanics | 13 | Scoring mechanics based on how the tile is destroyed (paper math for how the score is calulated based on chaining and tile collison).
21 | X |  | 1.5 | 0 | UI | 14 | Display current score.
22 | X |  | 0.5 | 0 | UI | 14 | Display current level & lives.
23 | 0 |  | 3 | 0 | Game - Juice | 15 | Implementing Various ball & paddle powerups.
24 | 0 |  | 0.75 | 0 | Game - Juice | 16 | Create Varying Particle Effects for Ball Launch and Grab.
25 | 0 |  | 0.75 | 0 | Game - Level | 17 | Implementing Environmental Hazards.
26 | 0 |  | 1 | 0 | Game - Level | 17 | Integrating Environmental Hazards into the levels.
27 | 0 |  | 1 | 0 | Testing | 28 | General Gameplay Testing
28 | 0 |  | 1 | 0 | Game - Data | 19 | Saving High Score Data to be persistent.
29 | 0 |  | 1 | 0 | UI | 20 | Refining/Updating Menus layouts.
30 | 0 |  | 0.75 | 0 | UI | 20 | Refining/Updating Menus assets.
31 | 0 |  | 1 | 0 | UI | 21 | Design Game over screen displaying your score and displaying all the high scores.
32 | 0 |  | 1 | 0 | UI | 21 | Adding Name to high Score list if a high score is beaten.
33 | 0 |  | 0.75 | 0 | UI | 21 | Return button to go back to main menu from the Game over screen.
34 | 0 |  | 1 | 0 | UI | 29 | Design Pause Menu
35 | 0 |  | 1 | 0 | UI | 29 | Functional Pause menu with option to return to main menu.
36 | 0 |  | 1 | 0 | Game - Mechanics | 22 | RNG based Power Drop on tile breaks.
37 | 0 |  | 1 | 0 | Testing | 28 | General Gameplay & UI functionality Testing
38 | 0 |  | 1 | 0 | Game - Audio | 23 | Adding in audio effects for different tiles breaking and background audio.
39 | 0 |  | 0.75 | 0 | Game - Audio | 24 | Audio for the Menus.
40 | 0 |  | 0.75 | 0 | Testing | 28 | Audio Testing with focus on audio overlaps & distortion.
41 | 0 |  | - | 0 | Game - Level | 25 | Adding in More levels if PCG is not used for infinite level generation.(Number & quality of levels depends on time).
42 | X |  | 1 | 0.25 | Game - Level | 27 | Create a chroma key for creating levels using paint.
43 | 0 |  | 1 | 0 | UI | 30 | Design Tutorials Menu dislaying various tile types and powers.
44 | 0 |  | 1 | 0 | UI | 30 | Integrating Tutorials Menu with main menu & pause menu.
45 | 0 |  | - | 0 | Game | 26 | Final polish and bug fixing.
46 | X | % | 2 | 2.18 | Game - Physics | 7 | Gameplay Physics for collisions between ball and paddle and ball and the tiles.
47 | X | % | 2 | 1 | Game - Level | 12 | Added in code architecture for generating Maps using images.
48 | X | % | 1 | 0.6 | Miscellaneous | 9999 | Data Driving Gameplay Camera configuration
49 | X | % | 2 | 1.5 | Game - Level | 12 | Generating map from Image
50 | / | % | 5 | 2.5 | Miscellaneous | 9999 | Adding in Gameplay Assets like Tiles, Ball, world , etc.
51 | 0 | % |  |  | #N/A
52 | 0 | % |  |  | #N/A
53 | 0 | % |  |  | #N/A
54 | 0 | % |  |  | #N/A
55 | / | % | 10 | 1.85 | Miscellaneous | 9999 | Engine Code/Slice of Life code that does not directly effect gameplay
|  |  | 80 | 22.29

## Sprints
Fields
Task Id | Unique id for sorting, searching, and grouping tasks
Status | Current status of this task, see legend
Estimate | Estimated time to complete this task, in hours
Actual | How much time was actually spent on this task, in hours
Feature Id | Unique id for sorting, searching, and grouping features
Description | Sufficient text to fully explain the how the feature works
Status Codes | Status meaning |  |  |  |  | Feature/Task Tags | Tag meaning
O | Not Started |  |  |  |  | * | Stretch Goal - Dependent on game feel / results post implementation
/ | In Progress |  |  |  |  | % | Not originally planned.
X | Complete |  |  |  |  | ! | Highest priority
< | Sent to backlog |  |  |  |  | x | Removed from original plan.
> | Carried to next sprint
D | Deleted
CURRENT SPRINT
DATE START | 2020-06-15 |  |  |  |  | DATE END | 2020-06-21
Task ID | Status | Task Tags | Estimate | Actual | Sub-Task Time | Feature Area | Feature ID | Original Task Description | Sub Task Description
1 | [5 empty] | Game - Level | 27
[6 empty] | Game - Level | 27
[6 empty] | Game - Data | 5
[6 empty] | Game - Level | 27
[6 empty] | Game - Level | 27
2 | [5 empty] | Game - Data | 5
[6 empty] | Game - Data | 5
[6 empty] | Game - Data | 5
[6 empty] | Game - Data | 5
3 | [5 empty] | Game - Physics | 7
4 | [5 empty] | Input | 1
5 | [5 empty] | Testing | 8
42 | [5 empty] | Miscellaneous | 9999
[6 empty] | Game - Level | 27
46 | [5 empty] | UI | 4
48 | [5 empty] | Game - Data | 5
[6 empty] | Miscellaneous | 9999
[6 empty] | Miscellaneous | 9999
49 | [5 empty] | Game - Level | 12
|  |  | 0 | 0
PAST SPRINTS
DATE START | 2020-06-01 |  |  |  |  | DATE END | 2020-06-07
Task ID | Status | Task Tags | Estimate | Actual | Sub-Task Time | Feature Area | Feature ID | Original Task Description | Sub Task Description
1 | X |  | 3 | 2.58 |  | Game - Level | 27 | Initial Test Level Setup
[5 empty] | 0.5 | Game - Level | 27 |  | Added in hardcoded map bounds , a paddle and Ball
[5 empty] | 0.33 | Game - Data | 5 |  | Fixed Orthographic Camera Aspect Ratio.
[5 empty] | 0.75 | Game - Level | 27 |  | Added in architecture for tiles , maps, paddle and ball as a factory style entity creation
[5 empty] | 1 | Game - Level | 27 |  | Added in some test tiles to test map.
2 | > |  | 2 | 2.33 |  | Game - Data | 5 | Data driving Tiles, Paddle & Ball
[5 empty] | 1.33 | Game - Data | 5 |  | Data Driving Tiles
[5 empty] | 0.25 | Game - Data | 5 |  | Created tileDefinitions XML file with every tile corresponding to a color key.
[5 empty] | 0.75 | Game - Data | 5 |  | Paper Calculation for Percentage size of individual Component like world bounds and tiles due to data driven camera
3 | D | x | 2 | 0.5 |  | Game - Physics | 7 | Simpler Physics system for collisions between ball and paddle and ball and the tiles.
4 | > |  | 0.5 | 0.5 |  | Input | 1 | Player controls Paddle with Mouse Movement.
5 | D | x | 2 | 0 |  | Testing | 8 | Updating Test Level & Stress testing Physics system for performance.
42 | X |  | 1 | 0.25 |  | Miscellaneous | 9999 | Create a chroma key for creating levels using paint.
[5 empty] | 0.25 | Game - Level | 27 |  | Created tileDefinitions XML file with every tile corresponding to a color key.
46 | X | % | 2 | 2.18 |  | UI | 4 | Gameplay Physics for collisions between ball and paddle and ball and the tiles.
[5 empty] | 0.33 | Testing | 8 |  | Hardcoded Physics for ball vs paddle and ball vs map bounds collisions.
[5 empty] | 1 | Game - Physics | 7 |  | removed hardcoded physics values and fixed certain collision bugs for correct ball reflection & tile collisions
[5 empty] | 0.1 | Game - Physics | 7 |  | Updated collisions to handle edge case of vertex collision
[5 empty] | 0.75 | Game - Physics | 7 |  | Added in collisions for Tiles.
47 | X | % | 2 | 1 |  | Game - Level | 12 | Added in code architecture for generating Maps using images.
48 | X | % | 1 | 0.6 |  | Game - Data | 5 | Data Driving Gameplay Camera configuration
[5 empty] | 0.1 | Miscellaneous | 9999 |  | Added support for setting Camera aspect and dimensions using XML
[5 empty] | 0.5 | Miscellaneous | 9999 |  | Camera Dimension based updation of map bounds.
49 | X | % | 2 | 1 |  | Game - Level | 12 | Generating map from Image
|  |  | 17.5 | 10.94
DATE START | 2020-06-08 |  |  |  |  | DATE END | 2020-06-14
Task ID | Status | Task Tags | Estimate | Actual | Sub-Task Time | Feature Area | Feature ID | Original Task Description | Sub Task Description
50 | > | % | 5 | 2.5 |  | Game - Level | 27 | Adding in Gameplay Assets like Tiles, Ball, world , etc.
[5 empty] | 1 | Miscellaneous | 9999 |  | Added and updated paddle, bound and ball assets.
[5 empty] | 1 | Miscellaneous | 9999 |  | Updating Ball to switch sprite based on Tile Color on collision
[5 empty] | 0.5 | Miscellaneous | 9999 |  | Generated Ball and Glare VFX spriteSheets out of individual sprites
13 | X |  | 4 | 6 |  | Engine | 9 | Implement 2D - Particle System
[5 empty] | 6 | Engine | 9 |  | added in infrastructure for ParticleSystem2D.
14 | > |  | 1 | 0.5 |  | Game - Physics | 7 | Create Particle Effects on ball-Tile Collision.
[5 empty] | 0.25 | Game - Juice | 10 |  | Tested 2D particle system.
[5 empty] | 0.25 | Game - Juice | 10 |  | Added Some particle effect with sprites on ball and tile collision.
55 | > | % | 10 | 1.85 |  | Miscellaneous | 9999 | Engine Code/Slice of Life code that does not directly effect gameplay
[5 empty] | 0.25 | Miscellaneous | 9999 |  | Added DrawUnfilledAABB2 for debugging of tiles.
[5 empty] | 0.1 | Miscellaneous | 9999 |  | add in std vector utility for emplace back.
[5 empty] | 0.75 | Miscellaneous | 9999 |  | added support for changing window & cursor icon correctly.
[5 empty] | 0.75 | Miscellaneous | 9999 |  | Added in custom cursor and icon.
49 | X | % | 2 | 0.5 |  | Game - Level | 12 | Generating map from Image
| > |  |  |  | 0.5 | Game - Level | 12 |  | Updated alignment of image in game when generating Map
|  |  | 22 | 11.35

## Journal
Fields
Task Id | Unique id for sorting, searching, and grouping tasks
Status | Current status of this task, see legend
Estimate | Estimated time to complete this task, in hours
Actual | How much time was actually spent on this task, in hours
Feature Id | Unique id for sorting, searching, and grouping features
Description | Sufficient text to fully explain the how the feature works
Status Codes | Status meaning |  |  |  |  | Feature/Task Tags | Tag meaning
O | Not Started |  |  |  |  | * | Stretch Goal - Dependent on game feel / results post implementation
/ | In Progress |  |  |  |  | % | Not originally planned.
X | Complete |  |  |  |  | ! | Highest priority
< | Sent to backlog |  |  |  |  | x | Removed from original plan.
> | Carried to next sprint
D | Deleted
DATE START | 2020-06-01
Task ID | Status | Task Tags | Estimate | Actual | Feature Area | Feature ID | Task Description
1 | 0 |  | 3 | 0.5 | Game - Level | 27 | Added in hardcoded map bounds , a paddle and Ball
1 | 0 |  | 3 | 0.33 | Game - Data | 5 | Fixed Orthographic Camera Aspect Ratio.
3 | 0 | x | 2 | 0.5 | Game - Physics | 7 | Simpler Physics system for collisions between ball and paddle and ball and the tiles.
4 | 0 |  | 0.5 | 0.5 | Input | 1 | Player controls Paddle with Mouse Movement.
46 | 0 | % | 2 | 0.33 | Testing | 8 | Hardcoded Physics for ball vs paddle and ball vs map bounds collisions.
48 | 0 | % | 1 | 0.1 | Miscellaneous | 9999 | Added support for setting Camera aspect and dimensions using XML
|  |  | 11.5 | 2.26
DATE START | 2020-06-04
Task ID | Status | Task Tags | Estimate | Actual | Feature Area | Feature ID | Task Description
1 | 0 |  | 3 | 0.75 | Game - Level | 27 | Added in architecture for tiles , maps, paddle and ball as a fatory style entity creation
46 | 0 | % | 2 | 1 | Game - Physics | 7 | removed hardcoded physics values and fixed certain collision bugs for correct ball reflection & tile collisions
42 | 0 |  | 1 | 0.25 | Game - Level | 27 | Created tileDefinitions XML file with every tile corresponding to a color key.
|  |  | 6 | 2
DATE START | 2020-06-06
Task ID | Status | Task Tags | Estimate | Actual | Feature Area | Feature ID | Task Description
2 | 0 |  | 2 | 1.33 | Game - Data | 5 | Data Driving Tiles
46 | 0 | % | 2 | 0.1 | Game - Physics | 7 | Updated collisions to handle edge case of vertex collision
2 | 0 |  | 2 | 0.25 | Game - Data | 5 | Created tileDefinitions XML file with every tile corresponding to a color key.
|  |  | 6 | 1.68
DATE START | 2020-06-07
Task ID | Status | Task Tags | Estimate | Actual | Feature Area | Feature ID | Task Description
1 | 0 |  | 3 | 1 | Game - Level | 27 | Added in some test tiles to test map.
46 | 0 | % | 2 | 0.75 | Game - Physics | 7 | Added in collisions for Tiles.
47 | 0 | % | 2 | 1 | Game - Level | 12 | Added in code arcchitecture for generating Maps using images ( needs further testing ).
48 | 0 | % | 1 | 0.5 | Miscellaneous | 9999 | Camera Dimension based updation of map bounds.
2 | 0 |  | 2 | 0.75 | Game - Data | 5 | Paper Calculation for Percentage size of individual Component like world bounds and tiles due to data driven camera
49 | 0 | % | 2 | 1 | Game - Level | 12 | Generating map from Image
|  |  | 12 | 5
DATE START | 2020-06-09
Task ID | Status | Task Tags | Estimate | Actual | Feature Area | Feature ID | Task Description
50 | 0 | % | 5 | 1 | Miscellaneous | 9999 | Added and updated paddle, bound and ball assets.
55 | 0 | % | 10 | 0.25 | Miscellaneous | 9999 | Added DrawUnfilledAABB2 for debugging of tiles.
49 | 0 | % | 2 | 0.5 | Game - Level | 12 | Updated alignment of image in game when generating Map
|  |  | 17 | 1.75
DATE START | 2020-06-12
Task ID | Status | Task Tags | Estimate | Actual | Feature Area | Feature ID | Task Description
50 | 0 | % | 5 | 1 | Miscellaneous | 9999 | Updating Ball to switch sprite based on Tile Color on collision
13 | 0 |  | 4 | 6 | Engine | 9 | added in infrastructure for ParticleSystem2D.
55 | 0 | % | 10 | 0.1 | Miscellaneous | 9999 | add in std vector utility for emplace back.
|  |  | 19 | 7.1
DATE START | 2020-06-13
Task ID | Status | Task Tags | Estimate | Actual | Feature Area | Feature ID | Task Description
14 | 0 |  | 1 | 0.25 | Game - Juice | 10 | Tested 2D particle system.
14 | 0 |  | 1 | 0.25 | Game - Juice | 10 | Added Some particle effect with sprites on ball and tile collision.
50 | 0 | % | 5 | 0.5 | Miscellaneous | 9999 | Generated Ball and Glare VFX spriteSheets out of individual sprites
55 | X | % | 10 | 0.75 | Miscellaneous | 9999 | added support for changing window & cursor icon correctly.
55 | X | % | 10 | 0.75 | Miscellaneous | 9999 | Added in custom cursor and icon.
|  |  | 27 | 2.5
DATE START | 2020-06-14
Task ID | Status | Task Tags | Estimate | Actual | Feature Area | Feature ID | Task Description
| 0 | % | #N/A | 1 | #N/A
| 0 |  | #N/A |  | #N/A
| 0 |  | #N/A |  | #N/A
|  |  | #N/A | 1